## 2023
Quarter | Back-end | Front-end
I/2023 | Building the main function for reslove Sudoku real-time | Build the commonly screen for the moblie application
II/2023 | Adding new function, integrate to the system | Adding new screens, integrate to the system
III/2023 | Ready for alpha and beta testing, fixing the bugs | Ready for alpha and beta testing, fixing the bugs
IV/2023 | Ready for production, fixing the bugs left Planning for improving the system and new function | Ready for production, fixing the bugs left Planning for improving the system and new function
| Goals | Goals
| Complete all the functions | Complete all the screens
| Integrate for complete mobile application | Integrate for complete mobile application
| Fixing production bugs | Fixing production bugs

## Q1-2023
Week |  |  | Sprint | Back-end | Front-end | Points (Estimation of points) | Status
Week 01 | 2023-01-02 | 2023-01-06 |  | Build the system | Build the system | 5 | Done
Week 02 | 2023-01-09 | 2023-01-13 | Sprint 1 | Create and test CI-CD workflow | Create and test CI-CD workflow |  | Done
Week 03 | 2023-01-16 | 2023-01-20 |  | Create Login API | Create login screen | 5 | Doing
Week 04 | 2023-01-23 | 2023-01-27 | Sprint 2 | Create Authenticate API | Integrate Authenticate API |  | Todo
Week 05 | 2023-01-30 | 2023-02-03 |  | Test the Login, Authenticate API | Test the Login, Authenticate API | 5 | Todo
Week 06 | 2023-02-06 | 2023-02-10 | Sprint 3 | Create the function for scanning pictures | Create the home screen |  | Todo
Week 07 | 2023-02-13 | 2023-02-17 |  | Create the function for processing pictures | Create the scanning screen | 5 | Todo
Week 08 | 2023-02-20 | 2023-02-24 | Sprint 4 | Create the function for processing pictures | Create the result screen |  | Todo
Week 09 | 2023-02-27 | 2023-03-03 |  | Create the function to reslove Sudoku | Integrate all current screen | 5 | Todo
Week 10 | 2023-03-06 | 2023-03-10 | Sprint 5 | Integrate with Front-end and testing | Integrate scanning and resloving Sudoku |  | Todo
Week 11 | 2023-03-13 | 2023-03-17 |  | Integrate testing | Integrate testing | 5 | Todo
Week 12 | 2023-03-20 | 2023-03-24 | Sprint 6 | Ready for QA | Ready for QA |  | Todo
Top 3 Quarter Goals |  |  |  | Goals | Goals
|  |  |  | Create scanning pictures function | Create all the screens
|  |  |  | Create resolve sudoku function | Integrate with Back-end
Integrate with Front-end